## HIS PM Toolkit Table of Content
TABLE OF CONTENTS
The development of HIS products for global use is supported by the U.S. President’s Emergency Plan for AIDS Relief (PEPFAR) through the U.S. Centers for Disease Control (CDC) TAP central mechanism under the terms of a cooperative agreement. These products are solely the responsibility of the funding recipients and do not necessarily reflect the views of the United States Government.
| PHASE 1: PROJECT IN DEVELOPMENT |  |  |  | PHASE 2: PRODUCTION |  | TOOLS / LINKS
STEP | 01 PREPARE | 02 PROJECT CHARTER - PLAN | 03 DESIGN AND DEVELOP | 04 TEST AND IMPLEMENT | 05 PROJECT OR PRODUCT DISPOSITION | 06 FINAL PROJECT/PRODUCT OVERVIEW AND ANNUAL OPERATIONS ASSESSMENT
| PROJECT PREPARATION | PROJECT CHARTER / PROJECT PLAN | DESIGN AND DEVELOP | TESTING & IMPLEMENTATION | PROJECT Transition | FINAL PRODUCT OVERVIEW AND ANNUAL OPERATIONS CHECKLIST
LINKS | Template Link | Template link | Template Link | Template Link | Template Link | Template Link
INTRODUCTION | EXECUTIVE SUMMARY | INTRODUCTION: PURPOSE OF PROJECT MANAGEMENT PLAN | INTRODUCTION: PURPOSE OF PROJECT DESIGN AND DEVELOPMENT PLAN | INTRODUCTION: IMPLEMENTATION AND TESTING PLAN | INTRODUCTION: PROJECT OR PRODUCT DISPOSITION PLANNING | INTRODUCTION: FINAL PRODUCT OVERVIEW AND ANNUAL OPERATIONS ASSESSMENT
|  | PROJECT AND PRODUCT OVERVIEW | PROJECT AND PRODUCT OVERVIEW | PROJECT AND PRODUCT OVERVIEW | PROJECT AND PRODUCT OVERVIEW
PROJECT DESCRIPTION | GOALS AND OVERVIEW
| PROJECT INFORMATION | PROJECT DESCRIPTION | PROJECT DESCRIPTION |  | SCOPE | FINAL PRODUCT DESCRIPTION
| FINANCIAL CONSIDERATIONS | [5 empty] | BUDGET TEMPLATE
|  | OBJECTIVES |  |  | OBJECTIVES
HIGH-LEVEL BUSINESS REQUIREMENTS: DEFINITION OF A SUCCESS
PROJECT REQUIREMENTS |  | REQUIREMENTS GATHERING PROCESS
|  | STAKEHOLDER REQUIREMENTS GATHERING PROCESS |  |  | STAKEHOLDER IMPACT
|  | REQUIREMENTS ANALYSIS AND VALIDATION PROCESS |  |  | TRANSITION PLANNING
IN-SCOPE FOR PROJECT
|  | OUT-OF-SCOPE FOR PILOT | INFORMATIONAL REQUIREMENTS
BUSINESS PROCESS OR WORKFLOW
TESTING
PURPOSE OF THE TEST CASE DOCUMENT
TEST CASE SPECIFICATION
DESCRIPTION
RESOURCES
PRECONDITIONS
POST CONDITIONS
FLOW OF EVENTS
INCLUSION/EXCLUSION POINTS
SPECIAL REQUIREMENTS
PROJECT ORGANIZATION | PROJECT GOVERNANCE | ROLES AND RESPONSIBILITIES |  | ROLES AND RESPONSIBILITIES | POINTS OF CONTACT
| PROJECT COMMUNICATIONS PLAN | COMMUNICATIONS MANAGEMENT |  | COMMUNICATIONS MANAGEMENT | NOTIFICATIONS AND COMMUNICATIONS
| PRELIMINARY PROJECT SCHEDULE AND WORK BREAKDOWN | PROJECT SCHEDULE MANAGEMENT
PROJECT CHANGE MANAGEMENT PROCESSES
|  | MAJOR DELIVERABLES/MILESTONES |  | MAJOR DELIVERABLES/MILESTONES
PROJECT SCHEDULE
| PRELIMINARY ACQUISITION PLAN |  |  |  | SYSTEM DISPOSITION
IMPLEMENTATION & DISPOSITION PLANNING |  | DEPLOYMENT PLAN | STAKEHOLDER REQUIREMENTS | IMPLEMENTATION SCHEDULE |  |  | GANTT CHART
|  |  | SOFTWARE REQUIREMENTS | SOFTWARE | SOFTWARE DISPOSITION |  | REQUIREMENTS GATHERING
SOFTWARE PERFORMANCE REQUIREMENTS
ARCHITECTURE OVERVIEW
DESIGN AND DEVELOPMENT CO-DESIGN PLANNING
|  |  | HARDWARE REQUIREMENTS | HARDWARE | EQUIPMENT DISPOSITION |  | HARDWARE INVENTORY
|  |  |  | FACILITIES NEEDED DURING IMPLEMENTATION | FACILITIES |  | SITE PREPAREDNESS CHECKLIST
|  |  | AVAILABILITY REQUIREMENTS | MATERIALS
|  | REQUIREMENTS ANALYSIS AND VALIDATION PROCESS |  | DOCUMENTATION | DATA DISPOSITION
RECORDS MANAGEMENT
|  |  |  | PERSONNEL REQUIREMENTS | PROJECT STAFF
STAFFING REQUIREMENTS
|  |  | TRAINING AND CAPACITY BUILDING | TRAINING PLAN
OUTSTANDING ISSUES
IMPLEMENTATION IMPACT
IMPLEMENTATION VERIFICATION AND VALIDATION
COMPLIANCE | COMPLIANCE REQUIREMENT PLANNING | POLICY AND LAW COMPLIANCE PLANNING | COMPLIANCE REQUIREMENTS | COMPLIANCE REQUIREMENTS
|  | TRANSITION AND PROJECT CLOSE DOWN PLANNING | QUALITY / ACCEPTABILITY PLANNING | TRANSITION PLANNING - ACCEPTANCE CRITERIA |  | ANNUAL OPERATIONS ASSESSMENT
PERFORMANCE ASSESSMENT
FINANCIAL PERFORMANCE
INNOVATION
ENTERPRISE ARCHITECTURE
SECURITY AND PRIVACY
RECOMMENDATIONS
Investment Manager Recommendations
USER/CUSTOMER ASSESSMENT
PROJECTS RISKS AND ISSUES MANAGEMENT |  | RISKS |  | RISKS AND CONTINGENCIES |  |  | RISKS, ISSUES AND CHANGES LOG
|  | RISK AND ISSUE MANAGEMENT |  | RISKS REVIEW
EVALUATION |  | EVALUATION PLANNING | MEASURING PROJECT SUCCESS | EVALUATION
APPROVALS | APPENDIX A: PROJECT PREPARATION APPROVAL | APPENDIX A: PROJECT MANAGEMENT PLAN APPROVAL | APPENDIX A: REQUIREMENTS PLAN APPROVAL | APPENDIX A: Project Implementation and Testing Plan Approval
REFERENCES |  | APPENDIX B: REFERENCES | APPENDIX B: PROJECT WORKFLOW OR ARCHITECTURE EXAMPLES | APPENDIX B: REFERENCES
KEY TERMS |  | APPENDIX C: KEY TERMS |  | APPENDIX C: KEY TERMS |  | APPENDIX A: KEY TERMS
APPENDIX D: LIST OF PROJECT MANAGEMENT SOFTWARE
INNOVATION RECOMMENDATIONS | APPENDIX B: ALTERNATIVES AND ANALYSIS

## Tool Pack Overview
|  |  | TOOL PACK OVERVIEW | [5 empty] | The development of HIS products for global use is supported by the U.S. President’s Emergency Plan for AIDS Relief (PEPFAR) through the U.S. Centers for Disease Control (CDC) TAP central mechanism under the terms of a cooperative agreement. These products are solely the sponsibility of the funding recipients and do not necessarily reflect the views of the United States Government.
Which Stage(s) is Artifact Most Useful?
|  |  | PHASE 1: DEVELOPMENT & IMPLEMENT |  |  |  | PHASE 2: PRODUCTION
Template Name | Navigate to template | Purpose | 01 PREPARE | 02 PROJECT CHARTER - PLAN | 03 DESIGN AND DEVELOP | 04 TEST AND IMPLEMENT | 05 PROJECT Transition - DISPOSITION PLANNING | 06 FINAL PRODUCT OVERVIEW & ANNUAL OPS ASSESSMENT | Artifact Original Source
Budget | Template | Supports budget planning for HIS projects | [6 empty] | Downloaded from: https://www2a.cdc.gov/cdcup/library/templates/default.htm
Gantt Chart | Template | Create project work plan listing activities and tasks | [6 empty] | Template Created for HIS PM Toolkit
Gantt Chart - Example | Template | Example of a Gantt chart | [6 empty] | Template Created for HIS PM Toolkit
Project Risk-Issues-Change Log | Template | Supports documentation of project risks, issues and changes | [6 empty] | Template Created for HIS PM Toolkit based on CDC UP tools and artifacts from University of Washington's Digital Initiatives Group and Jembi Health Systems
Requirements | Template | Supports documentation of project requirements | [6 empty] | Template Created for HIS PM Toolkit based on CDC UP tools and artifacts from University of Washington's Digital Initiatives Group and Jembi Health Systems
Hardware Inventory | Template | Supports inventory of hardware purchased for this project | [6 empty] | Based on CDC UP tools
Site Preparedness Checklist | Template | Supports site field visits to prepare for HIS projects
PM Software Guide | Template | A guide to software for project management, beyond Gantt charts
CDC UP Project Plan Template | Template | Original template for project planning, it's more complex than the Gantt Chart | [6 empty] | Downloaded from: https://www2a.cdc.gov/cdcup/library/templates/default.htm
CDC UP Change Management Log | Template | Original template for Change Management log | [6 empty] | Downloaded from: https://www2a.cdc.gov/cdcup/library/templates/default.htm

## Budget
PROJECT BUDGET TEMPLATE
Downloaded from: https://www2a.cdc.gov/cdcup/library/templates/default.htm
Project Name:
Project Manager Name:
Project Start Date:
|  |  | Part 1: Project Estimates | [6 empty] | Part 2: Refined Project Budget
|  |  | Total Best Case Estimate | Total Most Likely Estimate | Total Worst Case Estimate | Total Weighted Estimate | [6 empty] | Total Project Budget
|  |  | 310 | 445 | 875 | 494.1667 | [6 empty] | 200
Item | Description of Item or Activity Being Estimated | How it will be Acquired | Best Case Estimate | Most Likely Estimate | Worst Case Estimate | Weighted Average Estimate | Who estimated this item | Date Estimates Created | Links | Specs | Quantity Needed | Unit Cost | Total Project Cost | Notes/Links | Date Refined Budget Created | Links
Individual 1 | Role or salary |  | 100 | 150 | 300 | 166.6667 |  | 2001-01-01 |  |  | 2 | 100 | 200
Tablet | Product functionality (2) |  | 95 | 135 | 250 | 147.5 |  | 2001-01-02
Individual 3 | Product functionality (3) |  | 115 | 160 | 325 | 180 |  | 2001-01-03

## Gantt Chart
PROJECT PLANNING / GANTT CHART TEMPLATE
<PROJECT NAME> GANTT CHART | [9 empty] | In progress
Project Name: | [9 empty] | Big review period
Project Manager Name: | [8 empty] | 15 | Deliverable deadline with date in box
RACI Matrix
|  |  |  | RESPONSIBLE performs work | ACCOUNTABLE checks in can veto / approve | CONSULTED asked for input | INFORMED decision or output shared |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Notes
Task Number | Activity | Task | DELIVERABLE |  |  |  |  | Document Links | 2021-01-04 | 2021-01-11 | 2021-01-18 | 2021-01-25 | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-10 | 2021-05-17 | 2021-05-24 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-08-02 | 2021-08-09 | 2021-08-16 | 2021-08-23 | 2021-08-30
Major Activity
Task 1
Task 2
Task 3
Task 4
Major Activity
Task 1
Task 2
Task 3
Task 4
Major Activity
Task 1
Task 2
Task 3
Task 4
Major Task
Task 1
Task 2
Task 3
Task 4

## Gantt Chart - Example
EXAMPLE PROJECT PLANNING / GANTT CHART TEMPLATE
GANTT CHART | [9 empty] | In progress
Project Name: |  | Electronic Health Record - HIV Care | [7 empty] | Big review period / task push
Project Manager Name: |  | Elijah Banda | [6 empty] | 15 | Deliverable deadline with date in box
RACI Matrix
|  |  |  | RESPONSIBLE performs work | ACCOUNTABLE checks in can veto / approve | CONSULTED asked for input | INFORMED decision or output shared |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Notes
Task Number | Activity | Task | DELIVERABLE |  |  |  |  | Document Links | 2021-01-04 | 2021-01-11 | 2021-01-18 | 2021-01-25 | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-10 | 2021-05-17 | 2021-05-24 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-08-02 | 2021-08-09 | 2021-08-16 | 2021-08-23 | 2021-08-30
Identify Stakeholders
|  | Meet with Ministry of Health Informatics Department |  | Project Manager | bar: 2021-01-04
|  | Present at TWG |  | Project Manager |  | TWG | bar: 2021-01-11
|  | Draft list of participants |  | Project Manager | TWG | TWG | bar: 2021-01-18
|  | Ministry of Health sign off on list | Stakeholder list | MOH | MOH ID |  |  |  | 2021-01-25: 27
Create a Governance process
|  | Write out governance process |  | Project Manager |  | TWG, MOH | bar: 2021-02-01 to 2021-02-08
|  | Create governance workflow |  | Project Manager | bar: 2021-02-08 to 2021-02-15
|  | Review governance process |  | MOH | Project Manager | Project Manager | TWG | bar: 2021-02-15 to 2021-02-22
|  | Approve governance process |  | MOH | MOH |  | TWG |  | 2021-02-22: 24
Major Activity
Task 1
Task 2
Task 3
Task 4
Major Task
Task 1
Task 2
Task 3
Task 4

## Project Risk-Issues-Change Log
RISKS, ISSUES AND CHANGE LOG TEMPLATE
|  |  |  | DESCRIPTION |  |  |  |  | ACTION PLAN |  |  |  |  | RESOLUTION
TICKET # | CATEGORY | CURRENT STATUS | PRIORITY | Issue, Risk, or Change Description What is the challenge or change needed? | Why important? | Reported by | Date reported | Service, Site or Facility Affected | Assigned to Must be formally assigned | Date assigned | Assigned Tasks or Action Steps | Agreed deadline | Issue requires the following person to sign off | FINAL RESOLUTION & RESOLUTION | Date Resolved | Persons Informed of Resolution
ID |  | Overall |  | Workflow diagram was not clear |  | Mr. Banda | 2020-02-01 | Jan Hospital | Henry Makungwa | 2020-02-15 |  | 2016-06-01 |  | Chembe suggested a ticket system be developed at facilities | 2016-01-31
1 | Risk | Closed | Critical
2 | Issue
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
| . | . | . | . |  | . | . | . | . | . | . | . | . | . | . | .

## Requirements
PROJECT REQUIREMENTS TEMPLATE
note: this template has conditional formatting to support its use. Either download to use in Excel - or - follow these instructions to copy & move this sheet to another Google spreadsheet
Current Status | Prioritization | Requirement Number | Date Requirement Added | High Level Requirement | Module / Service | Specific Feature Name | User or role As a... | Detailed Requirement I need to... | Rationale So that... | If requirement is a software bug, how was this triggered? Describe the specifics so it can be replicated. | Quality Assurance: how will we measure that the requirement is met or working? | Link to Wireframe or Mock-up | Notes
Example | High | 1.1 |  | Role-based access | User Administration | Configure roles | Administrator | Assign users to multiple roles | A clinician who is an administrator can have full access
Example | Critical | 1.2 |  | Routine Reporting | HIV Care | Data exporting | M&E Coordinator | View and share quarterly report | Upload it to MOH for reporting |  | Validate | Report mockup
Retired/ Obsolete
Resolved
Retired/ Obsolete
Address in Future Version

## Hardware Inventory
HARDWARE INVENTORY TEMPLATE
HARDWARE INVENTORY
Project Name:
Project Manager Name:
Name/ ID | Type | Model/ Version | Physical Location | Equipment Owner (Person or Dept) | Maintenance Contract? Y/N | Maintenance Contact Point | Maintenance Type/ Level of Coverage | Maintenance Period Expiration Date | Required Licenses

## Site Preparedness Checklist
SITE PREPAREDNESS CHECKLIST
Site Preparedness Checklist
Adapted from EPLC Lite Tool
Basic Facility Information:
Facility Name
HMIS Facility Number
Date
Distance from DHO
Type of Facility
Catchment Population
Head Count
Respondent 1 Name | [9 empty] | FALSE | Facility in-Charge?
Title of Respondent 1
Address
Telephone
Email
Respondent 2 Name | [9 empty] | FALSE | Facility in-Charge?
Title of Respondent 2
Address
Telephone
Email
Checklist Question:
Power Supply
1. Does your facility currently have electrical power source?
| FALSE | Yes | FALSE | No
If Yes to No. 1 above, please place a tick next to the primary source of power:
| FALSE | Main power |  | FALSE | Solar |  | FALSE | Generator |  | FALSE | Other:____________
If yes to No.1 above please place a tick next to the backup source of power:
| FALSE | Main power |  | FALSE | Solar |  | FALSE | Generator |  | FALSE | Other:____________
Physical Infrastructure
4.Complete the table by putting an X against the type of type of physical security in place in each service area.
Service Area |  |  | Grilled doors |  | Barred windows |  | Lockable doors |  | Security guard |  | Lockable cabinets |  | Closed Circuit TV (CCTV)
Comments
ICT Infrastructure
5. Please place a tick next to the method of communication available at the site:
| FALSE | Cell phone |  | FALSE | Landline |  | FALSE | Radio | FALSE | Internet | FALSE | None | FALSE | Other
6. Does your facility have a Local Area Network (LAN)?
| FALSE | Yes | FALSE | No
Does your facility have Wifi connection?
| FALSE | Yes | FALSE | No
If none in place
7. Please place a tick next to the following items that your site has and indicate the quantity:
| FALSE | Computer (desktops) ____ |  |  |  | FALSE | Smart phones for work____ |  |  | FALSE | Tablets for work____ |  |  | FALSE | Card reader___
| FALSE | Computer (laptops) ___ |  |  |  | FALSE | Notebooks_____ |  |  | FALSE | Mouse |  |  | FALSE | Printer
| FALSE | UPS (uninterrupted power supply) _______
| FALSE | other, Specify ________________________________________________________
Service provision
8. Please place a tick next to the services your facility routinely provides:
| FALSE | Antenatal
| FALSE | Delivery
| FALSE | OPD
| FALSE | Child Health
| FALSE | Inpatient care, list wards__________________
| FALSE | TB
| FALSE | HIV Care (ART services)
| FALSE | HIV Testing
| FALSE | Non-communicable disease care, list: ___________________
| FALSE | Community Services
| FALSE | Outreach / mobile services
| FALSE | Laboratory
| FALSE | Pharmacy
| FALSE | Radiology
| FALSE | Other:_______________________________
| FALSE | Other:_______________________________
| FALSE | Other:_______________________________
| FALSE | Other:_______________________________
Human Resource
9. Please place a tick next to the members of staff present at your site and indicate how many are present:
| FALSE | Medical doctor_______ | [5 empty] | FALSE | Radiology personnel_______
| FALSE | Clinical officer ________ | [5 empty] | FALSE | Laboratory Personnel______
| FALSE | Physician Assistant _______ | [5 empty] | FALSE | Pharmacy Personnel_______
| FALSE | Nurse ______ | [5 empty] | FALSE | Community Health Worker ______
| FALSE | Midwife ______ | [5 empty] | FALSE | Data Entry Clerk_____
| FALSE | Traditional Birth attendant (TBA)________ | [5 empty] | FALSE | EHT?
| FALSE | Counselor________ | [5 empty] | FALSE | CDE?
| FALSE | Other (specify type and quantity):_______________
| FALSE | Other (specify type and quantity):_______________
| FALSE | Other (specify type and quantity):_______________
10. Please place a tick next to the members of staff present at your site and indicate how many are computer literate
| FALSE | Medical doctor_______ | [5 empty] | FALSE | Radiology personnel_______
| FALSE | Clinical officer ________ | [5 empty] | FALSE | Laboratory Personnel______
| FALSE | Physician Assistant _______ | [5 empty] | FALSE | Pharmacy Personnel_______
| FALSE | Nurse ______ | [5 empty] | FALSE | Community Health Worker ______
| FALSE | Midwife ______ | [5 empty] | FALSE | Data Entry Clerk_____
| FALSE | Traditional Birth attendant (TBA)________ | [5 empty] | FALSE | EHT?
| FALSE | Counselor________ | [5 empty] | FALSE | CDE?
| FALSE | Other (specify type and quantity):_______________
| FALSE | Other (specify type and quantity):_______________
| FALSE | Other (specify type and quantity):_______________
Management of patient records
11. Please tick all the patient information systems in place?
| FALSE | Individual single visit form__
| FALSE | Individual longitudinal visit form_______
| FALSE | Patient longitudinal registers_
| FALSE | Non standardized counter book registers
| FALSE | Other (specify):_______________
| FALSE | Other (specify):_______________
| FALSE | Other (specify):_______________
12. Are there any unique identifiers for patients?
| FALSE | Yes | FALSE | No
If Yes, provide details of the UID:
13. Are there any electronic patient management systems
| FALSE | Yes | FALSE | No
If Yes, describe:
System |  |  | Purpose |  |  | Funder |  |  | Currently working?
Note on J100: ====== ID#AAAAOgBJDho (2021-08-23 20:31:17) @ihj0@cdc.gov- do you know what these acronyms stand for? -Beth Dunbar

## PM Software Guide
PROJECT MANAGEMENT SOFTWARE GUIDE
Courtesy of JEMBI (Jan 2021)
SOFTWARE NAME | Features | Pros | Cons | Cost* *as of Jan 2021 | Example
Gantt Chart |  | - Runs on a browser - Collaborative features in real time - Saved in the cloud - No charge for web storage - Version control - Chat inbuilt - Help provided by google online - File format is documented - Publishing of sheets - Google Ads Scripts | - Gets slow with big datasets - Limited data visualization options - Limited formulas and functions - Limited customization options | Free with a google account | Example in PM Toolkit
CDC UP Project Plan Template (Example) |  | - Created in Excel or Google Spreadsheet - Useful to see all steps and autocalculations of times | May be complicated or hard to update | Free | Example in PM Toolkit
Asana | - Team management - Communication - Work, project and task management - Views - Reporting - Top integrations - Mobile - Customizable Dashboards - Notifications & Reminders - Active Feeds | - Customisation of the dashboards - Better Collaboration - Great storage security - Variety of integrations - It offers a free plan - Prioritization | - Limited exporting and importing functionality - No time tracking - Too many features - Task can only be assigned to one person - Not too friendly for new users - No Two-Factor Authentication | Basic -$0.00 for individuals or teams just getting started with project management. Its free forever Premium - $10.99 for teams Per user, per month billed annually. $13.49 billed per month Business - For teams and companies $24.99. Per user, per month billed annually $30.49 billed monthly
Redmine | - User self-registration support - News, document & files management - Multi Language support - Time tracking - Gantt chart and calendar - Multiple projects support - Flexible issue tracking system - Issues, Time-entries, Projects - Flexible role-based access control | - Open Source - Multi Project Management - Issue Tracking - Role-based access control - Time Tracking - Lots of incredible features eg project wikis, news, manage files, create custom fields etc | - Some of the dashboard features are tough to figure out - Lacks and overview project main indicators dashboard - It takes some time to become an expert | - Redmine is open source and released under the terms of the GNU General Public License v2 (GPL). - It is open Source, but some plugins can be paid.
MS Projects | - Communication and Collaboration - Reporting - Roadmap -Timesheets -Timeline view i.e Gantt chart - Board View i.e A Kanban board view for managing workflow and status - Grid View - Resource Management - Co-authoring between stakeholders and team members | - Allows using of templates that are ready to use - It is a desktop application which can even run in the absence of an internet connection - It has great reliability and support - It integrate with Microsoft Office Suite - It can be used for financial management - It is a veteran in the programming industry | - It is desktop - installed - It has a steep learning curve - It is expensive - It has compatibility issues - Its focus is general i.e it is not catered for specific projects - It has limited integrations - Not the best for agile - Poor progress visualization | MS Project Plan 1 - $10 / user per month MS Project Plan 2 - $30 / user per month MS Project Plan 3 - $55 / user per month
JIRA | - Agile development - Jira Project Tracking - Mobile applications - Reports in Jira - Jira Security - - Issue Creation - Roadmaps - Real - Time Notification - Activity Log - Issue Templates - Jira Dashboard - Time Tracking and Colour indication | - Easy to use - Across all mobile and desktop - Easy to learn - Highly customizable - Great for agile - It supports roadmap requirements - Available integration with many popular third-party software - Works for different types of users e.g developers, project managers, engineers etc | - Reports are not reusable - Limited file size upload - Confusing UI - Complex integration and migration from other application lifecycle management (ALM) systems - Not the best on mobile app compared with its web version | FREE - $0 Always free for 10 users STANDARD - $7 per user (average) $70 a month PREMIUM - $14 per user (average) $140 a month ENTERPRISE - Conduct the sales team about pricing for Cloud Enterprise
Wrike | -Organized File Management - Seamless Communication - Collaborative Editing - Easy Time Tracking - Reporting Using Real-time Data - Visual Timelines - Resource Management - Customizable Workflows | - Flexible project templates - Powerful proofing tool - Easy-to-use task management - Impressive Gantt chart - Improved visibility - Two-factor authentication support | - Missing note- taking tool - It's expensive for solo or small teams - The default filter cannot be changed - Missing chat option - Not good with integration such as Outlook etc | FREE - $0,00 . For a small teams 1 - 5 users PROFESSIONAL - $9.80 user/ month. Full project planning collaboration for 5, 10, 15 users BUSINESS - $24.80 user/month. ENTERPRISE - Contact the Wrike sales team
Smartsheet | - Drag-and-drop cards for quick sharing - Quick file attachments - Effective resource management - Create shareable reports - Automatic update requests - Filter item views - Customizable dashboard - Automated Reported - Project Templates - Gantt Cards - Alerts and reminders | - Easy to learn or use - Does more than just project management - Automated tasks and notifications - Visualization of key data metrics | - It's costly - Formatting and branding capabilities - Need to purchase additional "premium" applications in order to use the product to its full potential | Standard - Individual - R209 - Business - R373 per user/month Enterprise - Enterprise - contact sales team for pricing Premier - contact sales team for pricing
ClickUp |  |  |  | https://clickup.com/pricing
GitHub

## WireFrames and Mockup Software
WIREFRAME AND MOCK-UP
SOFTWARE NAME
Exclidraw
Draw.io
Balsamiq

## CDC UP Change Management Log
CDC UP CHANGE MANAGEMENT LOG
Downloaded from: https://www2a.cdc.gov/cdcup/library/templates/default.htm
Project Name: |  | <optional>
National Center: |  | <required>
Project Manager Name: |  | <required>
Project Description: |  | <required>
ID | Current Status | Priority | Change Request Description | Assigned To Owner | Expected Resolution Date | Escalation Required (Y/N)? | Action Steps | Impact Summary | Change Request Type | Date Identified | Assoc ID | Entered By | Actual Resolution Date | Final Resolution & Rationale
| Open | Critical | EXAMPLE: Request for product functionality increase |  |  | Yes | EXAMPLE: Analyze impact of requested change and then meet with the change control board (CCB) to present findings for final decision on the requested change | EXAMPLE: Project scope, schedule, resources, and potentially budget may all be impacted | Product | 2006-01-01 |  |  |  | EXAMPLE: The CCB has approved the change
| Work In Progress | High | EXAMPLE: The schedule slipped due to unexpected weather related events |  |  | No | EXAMPLE: Adjust the schedule to account for the weather related events | EXAMPLE: Project schedules, resources, and possibly budget may all be impacted | Project | 2006-01-01 |  |  |  | EXAMPLE: Updated schedule reviewed and approved
| Closed | Medium | [6 empty] | Other
Low

## CDC UP Project Plan Template
CDC UP PROJECT PLAN TEMPLATE
Downloaded from: https://www2a.cdc.gov/cdcup/library/templates/default.htm
Project Schedule
Refer to the CDC_UP_Microsoft_Project_Practices_Guide.doc for template information that should be updated prior to using this template.
Project Name:
Project Manager Name:
Project Start Date:
Project Schedule Last Updated Date:
ID | Task Name | Duration |  | Baseline Start | Expected Start | Actual Start | Baseline Finish | Expected Finish | Actual Finish | Baseline Work |  | Actual Work |  | Remaining Work |  | % Complete | EAC |  | EAC Variance |  | Predecessors | Resource Names
0 | CDC UP Project Schedule Template (Example) | 33 | days | NA | 2007-01-01 | NA | NA | 2007-02-09 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs
1 | Project Management Activities | 3 | days | NA | 2007-01-01 | NA | NA | 2007-01-02 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs
2 | Complete Project Charter | 1 | days | NA | 2007-01-01 | NA | NA | 2007-01-01 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs
3 | Complete Project Management Plan | 1 | days | NA | 2007-01-02 | NA | NA | 2007-01-02 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 2
4 | Conduct Monitoring & Controlling Activities | 1 | days | NA | 2007-01-01 | NA | NA | 2007-01-01 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs
5 | UP Management Activities Completed | 0 | days | NA | 2007-01-01 | NA | NA | 2007-01-01 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs
6 | Initiation/Planning | 3 | days | NA | 2007-01-01 | NA | NA | 2007-01-03 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs
7 | Conduct Feasibility Study | 1 | days | NA | 2007-01-01 | NA | NA | 2007-01-01 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs
8 | Complete Business Case | 1 | days | NA | 2007-01-02 | NA | NA | 2007-01-02 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 7
9 | Complete Project Planning | 1 | days | NA | 2007-01-03 | NA | NA | 2007-01-03 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 8
10 | Initiation/Planning Activities Completed | 0 | days | NA | 2007-01-03 | NA | NA | 2007-01-03 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 9
11 | Requirements Analysis | 2 | days | NA | 2007-01-04 | NA | NA | 2007-01-05 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs
12 | Complete Requirements Gathering | 1 | days | NA | 2007-01-04 | NA | NA | 2007-01-04 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 10
13 | Complete Security Planning | 1 | days | NA | 2007-01-05 | NA | NA | 2007-01-05 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 12
14 | Requirements Analysis Completed | 0 | days | NA | 2007-01-05 | NA | NA | 2007-01-05 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 13
15 | Design | 4 | days | NA | 2007-01-08 | NA | NA | 2007-01-11 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs
16 | Complete High-Level Design | 1 | days | NA | 2007-01-08 | NA | NA | 2007-01-08 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 14
17 | Complete Proof of Concept | 1 | days | NA | 2007-01-09 | NA | NA | 2007-01-09 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 16
18 | Complete Detailed Design | 1 | days | NA | 2007-01-10 | NA | NA | 2007-01-10 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 17
19 | Complete Technical Specification | 1 | days | NA | 2007-01-11 | NA | NA | 2007-01-11 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 18
20 | Design Completed | 0 | days | NA | 2007-01-11 | NA | NA | 2007-01-11 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 19
21 | Development | 8 | days | NA | 2007-01-12 | NA | NA | 2007-01-23 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs
22 | Complete Build/Develop | 1 | days | NA | 2007-01-12 | NA | NA | 2007-01-12 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 20
23 | Complete Integration Planning | 1 | days | NA | 2007-01-15 | NA | NA | 2007-01-15 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 22
24 | Complete Documentation | 1 | days | NA | 2007-01-16 | NA | NA | 2007-01-16 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 23
25 | Complete Test Planning | 1 | days | NA | 2007-01-17 | NA | NA | 2007-01-17 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 24
26 | Complete Deployment Planning | 1 | days | NA | 2007-01-18 | NA | NA | 2007-01-18 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 25
27 | Complete Training Planning | 1 | days | NA | 2007-01-19 | NA | NA | 2007-01-19 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 26
28 | Complete Business Continuity Planning | 1 | days | NA | 2007-01-22 | NA | NA | 2007-01-22 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 27
29 | Complete Transition Planning | 1 | days | NA | 2007-01-23 | NA | NA | 2007-01-23 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 28
30 | Development Completed | 0 | days | NA | 2007-01-23 | NA | NA | 2007-01-23 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 29
31 | Test | 6 | days | NA | 2007-01-24 | NA | NA | 2007-01-31 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs
32 | Complete Unit test | 1 | days | NA | 2007-01-24 | NA | NA | 2007-01-24 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 30
33 | Complete Function Test | 1 | days | NA | 2007-01-25 | NA | NA | 2007-01-25 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 32
34 | Complete Integration Test | 1 | days | NA | 2007-01-26 | NA | NA | 2007-01-26 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 33
35 | Complete Regression Test | 1 | days | NA | 2007-01-29 | NA | NA | 2007-01-29 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 34
36 | Complete System Test | 1 | days | NA | 2007-01-30 | NA | NA | 2007-01-30 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 35
37 | Complete User Acceptance Test | 1 | days | NA | 2007-01-31 | NA | NA | 2007-01-31 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 36
38 | Test Completed | 0 | days | NA | 2007-01-31 | NA | NA | 2007-01-31 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 37
39 | Implementation | 3 | days | NA | 2007-02-01 | NA | NA | 2007-02-05 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs
40 | Complete Deployment | 1 | days | NA | 2007-02-01 | NA | NA | 2007-02-01 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 38
41 | Complete Training | 1 | days | NA | 2007-02-02 | NA | NA | 2007-02-02 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 40
42 | Complete Support | 1 | days | NA | 2007-02-05 | NA | NA | 2007-02-05 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 41
43 | Development/Implementation Completed | 0 | days | NA | 2007-02-05 | NA | NA | 2007-02-05 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 42
44 | Operations & Maintenance | 2 | days | NA | 2007-02-06 | NA | NA | 2007-02-07 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs
45 | Complete Operations Activities | 1 | days | NA | 2007-02-06 | NA | NA | 2007-02-06 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 43
46 | Complete Maintenance Activities | 1 | days | NA | 2007-02-07 | NA | NA | 2007-02-07 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 45
47 | Operations & Maintenance Completed | 0 | days | NA | 2007-02-07 | NA | NA | 2007-02-07 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 46
48 | Disposition | 2 | days | NA | 2007-02-08 | NA | NA | 2007-02-09 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs
49 | Complete Archive | 1 | days | NA | 2007-02-08 | NA | NA | 2007-02-08 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 47
50 | Complete Disposal | 1 | days | NA | 2007-02-09 | NA | NA | 2007-02-09 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 49
51 | Retirement Completed | 0 | days | NA | 2007-02-09 | NA | NA | 2007-02-09 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 50
52 | Project Completed | 0 | days | NA | 2007-02-09 | NA | NA | 2007-02-09 | NA | 0 | hrs | 0 | hrs | 0 | hrs | 0% | 0 | hrs | 0 | hrs | 51

## Project Health Checklist (hidden)
*Adapted for JEMBI
PROJECT HEALTH CHART
Project Name:
Prepared by
Date
Seven Key Questions
This section introduces the seven key questions which can be used to assess a project’s health. These questions can be used for a quick assessment of a project and can be asked informally. I suggest that these questions be used by Project Sponsors or key stakeholders if they do not understand the status of a project.
Question 1: What’s the Vision?
Ask this question of those in charge and those being charged. Ideally, the vision can be articulated at all levels of the project organization. If those in charge cannot clearly articulate the Vision in a few short sentences, I would question whether anyone on the project really understands the objectives of the project. A misunderstood Vision can lead to confusion, frustration, distraction, and of course, scope sickness. If you ask this question of the team members, do the team members understand the significance of their contributions to the Vision?
I believe that the Vision of the project is one of the most critical factors for success. Developing the Vision is a critical exercise in communications between the Project Sponsor, the Project Manager, and the Project Stakeholders. As Winnie the Pooh says, “Before beginning a hunt, it is wise to ask someone what you are looking for before you begin looking for it.” (Winnie the Pooh quotes, 2005)
Question 2: Who’s in charge?
This question speaks directly to the leadership of the project. Who is really leading the project? Are the leaders leading or being led? Who is providing direction and decision-making? Are the lines of communication and decision-making clearly defined? Is there one decision maker clearly in charge or do decisions get made by committee? If decisions are made by committee, is the committee effective in making decisions?
Question 3: What’s expected?
Ask this question of those in charge and those being charged. Missed expectations can lead to a perception that an otherwise well-executed project is failing or has failed. Are the expectations of the client clearly understood? Are the expectations of the individual team members also clearly defined? Poorly defined expectations can lead to missed budgets, missed schedules, rework, and poor team morale.
Question 4: What’s the risk?
Ask this question of those in charge and those being charged. The plan can’t possibly be considered complete if the risks to project success are not clearly understood; yet, many projects are often started without the identification of key risks. Just as important as identifying risks is the awareness of risks by all team members. If the individual team members do not understand the key risks, the probability of those risks occurring increases.
Question 5: Who’s doing what?
Are roles and responsibilities clearly defined? Are the right resources doing the right things at the right time? If confusion exists over roles or assignments, this can lead to missed milestones, rework situations, missed objectives, and eventually, a failed project.
Question 6: How are we doing it?
Ask this question to understand if the project team is using a system or methodology for executing the project and producing results. Does the team embrace the system or methodology or consider it an impediment to success? A solid system is built on trust and can empower the team to do what is required to be successful. A solid system will allow team members to be more effective than they could be without the system.
Question 7: What happens if...?
What happens if something changes? This question helps to frame the project team’s ability to absorb and manage change. Change happens, but what is critical to the project’s success is how the team reacts to change. “Freezing” change from occurring is not always the answer. Managing change and balancing change against conflicting priorities and objectives is critical. A system or methodology for managing change embraced by all stakeholders ensures that change will be managed effectively.
A Healthcheck Process
A Healthcheck process can improve the overall health of projects in an organization. The process can lead to a higher quality of execution and to an improved success rate. This section introduces the Healthcheck process by addressing the “what, how, and how often” of the process.
What
A Healthcheck process is a brief review of the project by a party external to the project. The process can be performed by a peer manager, an external entity, the project sponsor, or, if it exists in the organization, by a Project Management Office (PMO). I recommend that the review be brief. The process can be as simple as asking a few key questions (such as the seven listed above) or by using a more formal list of questions.
If used effectively, a Healthcheck process can provide a “clean bill of health” or identify areas requiring attention. A Healthcheck can and should initiate an action plan to address found symptoms.
How
1. Schedule the Healthcheck.
2. Request and review key documents (Vision Statement, Project Charter, Scope, etc.).
3. Ask key questions.
4. Complete the checklist (or survey).
5. Document the results.
6. Determine a plan of action (if needed).
How Often
• Schedule periodic Healthchecks. Schedule them more often for complex or long-term projects.
• Conduct unscheduled Healthchecks. All though the timing of these may be a surprise, these should be expected as “standard operating procedure.” If you’re the project manager, expect to be surprised every now and then.
• Allow Healthchecks to be requested by your management, by your customer, or by any key stakeholder. If requested, schedule and conduct the Healthcheck promptly. The Checklist and Questions
Communications
The purpose of this section should be to determine if communications, leadership, and management are clearly in place. Some specific questions to be included in the checklist are the following:
1. Does the project have a documented Vision Statement?
2. Do all team members understand the Vision?
3. Has a Communications Plan been developed for the project? Some open ended questions to be asked should include questions of leadership style, team communications, and expectations.
Integration
The purpose of this section should be to determine if a plan has been documented and is being followed. Some specific questions to be included in the checklist are the following:
1. Does the project have a documented project plan?
2. Is the project plan used as the basis for tracking progress and making decisions?
3. Has a change process been implemented and is it being used? Open ended questions should focus on the team’s acceptance of the plan and the change management processes.
4. Scope
5. The purpose of this section should be to determine if the scope is defined well enough to lead to project success. Specific questions to be included in the checklist are the following:
1. Has a scope statement been documented?
2. Has a scope management plan been documented?
3. Are scope changes clearly identified? Open ended questions can help determine the team’s awareness of scope, impact of scope change, and an understanding of expectations.
4. Time
The purpose of this section should be to determine if the schedule has been defined well enough to lead to project success. Specific questions to be included in the checklist are the following:
1. Has the schedule been documented?
2. Does the schedule include milestones?
3. Is there a system in place to measure progress? Open ended questions can help determine the team’s awareness of the schedule and progress.
Cost
The purpose of this section should be to determine if costing processes have been developed and whether the project is maintaining cost objectives. Specific questions to be included in the checklist are the following:
1. Has a budget been documented?
2. Are actual expenses tracked against budgeted expenses?
3. Are cost forecasts regularly developed? Open ended questions can help determine the awareness of the budget, project “run-rates,” and the forecast.
4. Risk
5. The purpose of this section should be to determine if Risks have been identified and managed. Specific questions to be included in the checklist are the following:
1. Have the key risks been identified?
2. Has a Risk Management plan been documented?
3. Has a Risk Response plan been documented?
• Quality
• The purpose of this section should be to determine if quality measures are in place for both the project and the product of the project. Specific questions to be included in the checklist are the following:
1. Has a quality plan been developed?
2. Are systems or methodologies in place to help improve the quality of the project and the product?
• Human Resources
• The purpose of this section should be to determine if resources are properly being used on the project. Specific questions to be included in the checklist are the following:
1. Has a resource plan been documented?
2. Have roles and responsibilities been clearly defined? Open ended questions should help determine an awareness of roles and the team morale. Procurement The purpose of this section should be to determine if processes are in place to manage interaction with the vendors and suppliers. Specific questions to be included in the checklist are the following:
3. Have contracts been approved for all participating vendors?
4. Are Statements of Work (SOW’s) in place for all vendors providing services to the project?