## I-LEAD Summary
Last updated:
Dates
Location
Venue
Participant country
Stakeholders
Request for nomination and the scope and purpose
Invitation letter with names
Focal point for country
Date for the invitations
Lead for the invitation
Co-signers for the Invitation
Facilitators and presenters
Implementation team (for logistics)

## Work Plan
Activities & Tasks | Responsible | Accountable | Consulted | Informed | Status | Start date | End date | Deliverable | Notes
Country Engagement
Host orientation call for Q&A with country stakeholders
Adapt/enhance and send standard concept note along with standard email
Adapt and send email to relevant country stakeholders
Confirm country stakeholder commitment
Confirm host role (e.g., facilitation, participation only, other)
Confirm I-LEAD dates
Identify in-country POC
Confirm opening speaker
Obtain opening speaker slides (if any)
Confirm closing speaker
Obtain closing speaker slides (if any)
Identify country facilitator(s)
Conduct country facilitator(s) training
Identify country presentors
Conduct presentation training/orientation
Obtain presenter slides
Venue & Catering
Determine and adapt general venue requirements
Identify and procure venue
Schedule monthly coordination calls with venue
Determine and provide seating arrangements for main and breakout rooms
Determine and provide wifi, lighting, projector, laptops, etc. needs
Schedule a walk through
Schedule a meeting space for the day before I-LEAD start
Determine and procure catering (venue or non-venue)
Participant Country Engagement
Inform POCs and stakeholders
Adapt and send standard letters of interest
Conduct sensitization session
Confirm final participant list (full name and email)
Request country requirements for meeting implementation
Participants
Adapt and send standard official invitation letter to participants
Send meeting invitation to participants
Request participant bios
Request ISHO assessment results
Request countries presentations
Request countries BYODD
Follow up on participant bios
Follow up on countries ISHO submissions
Follow up on countries presentation
Follow up on countries BYODD
Pre I-LEAD Events
Info session
Determine date for Info session
Identify and confirm speakers for Info session
Obtain/review/adapt slides for Info session
Send Info session calendar invite to POCs
Conduct Info session
Send post Info session email with recording, slides, next steps
Orientation
Determine date for Orientation session
Identify and confirm speakers for Orientation session
Obtain/review/adapt Orientation session slides
Send Orientation session calendar invite to POCs
Conduct Orientation session webinar
Identify high-level issues to tackle during I-LEAD
Send post Orientation session email with recording, slides, next steps
ISHO session
Determine date
Identify and confirm speakers for ISHO session
Obtain/review/adapt ISHO session slides
Send ISHO session calendar invite to POCs
Conduct ISHO session
Send post ISHO session email with recording, slides, next steps
Curriculum & Speakers
Identify participants for agenda development (host country, SMEs, other)
Determine sessions cadence and send meeting invite for agenda development workshop
Conduct agenda development workshop (and review high-level country issues)
Identify trainers/SMEs for training sessions
Finalize the agenda
Review/update glossary for technical terms
Combine speaker and participant bios into participant packet
Create and send meeting invites to virtual speakers
Obtain slides and materials from speakers for sessions
Planning session for facilitators/trainers, meeting with POCs
Send guidance to speakers and facilitators (practice speaking slowly, etc.)
Travel & Lodging (if necessary)
Secure approved hotel lodging rate
Send lodging information to participants
Procure shuttles for transport to I-LEAD venue
Translation & Interpretation (if necessary)
Adapt the translation and interpretation strategy and plan
Procure translation services
Procure interpretation services
Confirm translation of all materials using materials tracker
Confirm translated materials are stored in Google participant folders
Confirm space at venue for interpreter
Send materials to interpreter 7 days prior to I-LEAD
Confirm set up time with the interpreter
Event Logistics
Week Before I-LEAD
Confirm meeting space for in-person facilitator planning meeting
Print materials
Bring badges, pens, lanyards
Create end of day evaluation feedback forms
Create Google folder for photos
Finalize catering plan
Print participant certificates
Assign responsibilities in the "agenda tasking" tab
Day Before I-LEAD
Conduct in-person facilitator planning meeting
Walkthrough of the venue
Confirm table / seating arrangements
Confirm catering is ready to go
Confirm wifi, lighting, projector, laptops, etc. are working
Layout pens, notebooks, etc.
Arrange check-in station with sign-in sheet, name badge, lanyards
Print or buy any remaining materials
Review Facilitator's Guide
Create QR codes for end of day evaluation forms
During I-LEAD
Review "agenda tasking" tab responsibilities
Take photos and add in Google folder
Utilize Facilitator's Guide
Review end of day feedback and implement for next day as feasible
Take note of key takeaways, questions, etc.
Post I-LEAD
Send follow up email to participants with links to resources, etc.
Review evaluations for feedback and continuous improvement
Develop trip report with key takeaways, feedback summary, etc.

## Materials Tracker
Content | Source Language | Target Language | Details | Owner | Status | Cleared by | Phase Needed | Date Due | File | File type | Priority | Notes

## Agenda at a Glance v1 (hidden)
Time | Session Type | Monday September 5 | Tuesday September 6 | Wednesday September 7 | Thursday September 7 | Friday September 9 | Facilitators: 11
| Learning objective | Welcoming the participants Context setting for I-LEAD Country background | Identifying the main priority based on the context and situation in-country | Moving from current state to future state - how can we do it as a country? | Turning the discussions into solutions Developing country action plan Work on the presentation and outbrief | Thanking the participants Country presentations Country panel for closing remarks and key takeaways
8:30 - 9:00 | Check in Coffee/tea
9:00 - 11:00 | Plenary | Opening Remarks (PCO/PARCA/Julianna and Herman) Introduction to Informatics Capacity Development – From Vision and Strategy to Operations and Tactics | Leading and Managing an Informatics Savvy Health Organization (ISHO) Link | Using Design Thinking for Informatics Problem Solving Link | Plenary: Creating and Revisiting Value Claims for Health Information Systems and Activity Link | Plenary: Sharing Lessons Learned, Synthesis, and Next Steps/Action Steps (country outbrief)
| Room | Plenary Room | Plenary Room | Plenary Room | Plenary Room | Plenary Room
| Facilitator | TBD | TBD | TBD | TBD | TBD
11:00 - 11:30 | Coffee/Tea Break
11:30 - 12:30 | Plenary OR Q&A | Informatics Problem-Solving Link | Q&A, setting in | Q&A, setting in | Plenary: Decision-Making in Complex Settings with example walk-through Examples ADD LINK | Fill out and submit Google form Jeopardy game?
| Room | Plenary Room | Plenary Room/ Breakout room | Plenary Room/ Breakout room | Plenary Room/ Breakout room | Plenary Room
| Moderator | TBD | TBD | TBD | TBD
12:30 - 1:30 | Lunch
1:30 - 3:30 | Breakout groups | Country Context Presentations and Q&A for each country | Breakout groups: Identify the main priority the team will focus on | Breakout groups: Country Action Plan Development: Current State to Future State | Breakout groups: solutions and next steps, how will we measure success Countries create presentation here | Closing remarks (1 participant from each country and I-LEAD team) Closing remarks (Julianna/Herman, ILEAD team) Award certificates and group photo
| Room | Plenary Room | Breakout room | Breakout room | Breakout room | Plenary Room
| Facilitator (3 people) | Thailand: Phillippines: Vietnam: | Thailand: Phillippines: Vietnam: | Thailand: Phillippines: Vietnam: | Thailand: Phillippines: Vietnam: | Sam Hanna
3:30 - 3:45 | Break
3:45 - 4:45 | Report back, Q&A | Country Context Presentations and Q&A for each country (can shorten if needed) | Country discussion panel: 1-2 representatives from each country going over their experience | Report out from breakout groups | Report out from breakout groups
| Room | Plenary Room
| Moderator | TBD | TBD | TBD | TBD
4:45 - 5:00 | Evaluation of the day | Fill out and submit Google Form | Fill out and submit Google Form | Fill out and submit Google Form | Fill out and submit Google Form
| Room | Plenary Room | Plenary Room | Plenary Room | Plenary Room
Facilitator

## Agenda at a Glance
| Session Type | Monday, Month Day | Tuesday, Month Day | Wednesday, Month Day | Thursday, Month Day | Friday, Month Day | Facilitators: X
| Learning objective | Welcoming the participants Context setting for I-LEAD Country background | Identifying the main priority based on the context and situation in-country | Moving from current state to future state - how can we do it as a country? | Turning the discussions into solutions Developing country action plan Work on the presentation and outbrief | Thanking the participants Country presentations Country panel for closing remarks and key takeaways
8:30 - 9:00 | Check in Coffee/tea
9:00 - 10:00 | Session 1
Room
Facilitator
10:00 - 11:10 | Session 2
Room
Facilitator
11:10 - 11:30 | Coffee/Tea Break
11:30 - 12:30 | Session 3
Room
Facilitator
12:30 - 1:30 | Lunch
1:30 - 2:30 | Session 4
Room
Facilitator (3 people)
2:30 - 3:30 | Session 5
Room
Facilitator (3 people)
3:30 - 3:45 | Break |  |  |  |  | Evaluation
3:45 - 4:45 | Session 6
Room
Moderator
4:45 - 5:00 | Evaluation of the day
Room
Facilitator

## Roles and Responsibilities
| Country support team | Notes on roles | HQ Planning team | Notes on roles
Country
Country I-LEAD Primary POC
Country HIS POC
Country HIS POC
Country HIS POC
Country HIS POC
PCO
HQ Facilitator
Country Facilitator
Moderator
Backup HQ Facilitator
I-LEAD participant
I-LEAD participant
I-LEAD participant
Country confirmation
Next step

## Participants
Country | Name | Email | Organization | Title | Role | Bio | Visa Letter | Visa | eCC | Hotel | Flight | Hotel (optional!!) | Arrival date/time

## Agenda tasking
Date | Start time | End time | # | Session | Session Type | Room | Session lead | Session Lead Email | Slides/Materials | AV/Computer support | Note Taker | Contributors | Notes

## Speaker list tracker
Session | Session breakout | Speakers/Facilitators | Email | Responsible Person(s) (Joint Organizing Committee) | Confirmed (Yes/No/Tentative) | Content Coordination/Content Review Completed | Emerging Issues/Comments | Outlook Zoom Link Shared (Date Completed)
Site visit
Day 1
Break
Lunch
Day 2
Break
Lunch
Break
Day 3
Break
Lunch
Day 4
Break
Lunch
Break
Day 5
Break

## Implementation (hidden)
Last update: 4/17/2024
2024 Asia I-LEAD - Workplan: September 9 - 13
| Activities | Responsible | Supporting | Date Due | Status | Notes
1 | Pre-training preparation/Planning
| Secure venue (USAID ARTC) | Adeola |  | 2024-03-01 | Completed
| Conduct an analysis of travel logistics (visas needed etc.) | Adeola
| Receive preliminary committment by country teams to attend | Country HQ HIS POCs |  | 2024-04-17 | In Progress | Philippines: Djibril is checking
| Draft official invitation email | Anja |  |  | Completed
| Review the email draft with the interagency team | Anja |  |  | Completed
| Send the invitation to country teams | Anja |  |  | Completed | Who will be sending? Each country is different, four drafts
| Obtain confirmation of country attendence | Anja |  |  | Completed
| Finalize the list of participants from each country | I-LEAD POC |  |  | In progress
| Identify in-country POC(s) | Anja |  |  | Completed
| Draft invitation letters to candidates | Anja |  |  | In progress
| Tour of ARTC with ARTCs staff and PATH | Adeola |  |  |  | Friday before I-LEAD? Anja and Adeola should participate
Develop tailored briefing/sensitization material
Create a one-page document and distribute it to stakeholders with translation into necessary languages
Articulate scope for ILEAD: target audience, competencies covered, partners and stakeholders with indicating their roles
Develop a needs assessment tool for key informants and distribute it to stakeholders (in necessary languages)
Develop a participant information packet
PCO and Agency-level Leadership sensitization/approval
Hold standing meetings with all parties engaged to implement the workshop
Identify in-country POC
Develop messaging for in-country POC
Monitor country team progress
Compile high-level country issues to address in I-LEAD
Review high-level country issues to address in I-LEAD
2 | Select and Recruit Participants
| Identify the POC & agency POCs for questions regarding the workshop |  |  |  |  | Serves as overall point person for I-LEAD coordination, enables interagency communication
Meeting with key informants from different countries to identify high-priority topics specific to each country.
| Identify potential participants (USG, MOH, IPs) |  |  |  |  | Based on country issues, stakeholder groups
| Attend orientation webinar conducted by USG HQ |  |  |  |  | Kick-off point for I-LEAD work and participant expectation setting
| Identify high-level issues to tackle during I-LEAD |  |  |  |  | Aids in selecting participants and developing initial agenda
| Review materials for action items/homework |  |  |  |  | The participating team will have an internal plan/agreement to review, do, discuss, agree and submit the homework before the I-LEAD
| Conduct joint ISHO assessment (all participants) |  |  |  |  | Provide an opportunity to collaborate, build rapport, identify and prioritize the informatics gaps they want to focus
Finalize ISHO results, country presentation and BYODDs
Convene participants to develop country presentation and BYODDs
3 | Curriculum Development
Develop the I-LEAD Orientation agenda
Develop curriculum for the I-LEAD orientation
Incorporate feedback from the past I-LEAD session (September)
Analyze and summarize the feedback from the needs assessment
| Develop and validate a list of competencies, learning objectives, training modalities, supplementary learning materials | CDC - Neranga
| Determine if translation will be needed | CDC - Maria
Develop curriculum content, activities for sessions
Identify existing resources, adapt as necessary
Identify case studies with relevance to region
Develop I-LEAD Program Overview document
| Identify agenda manager/POC | CDC - Maria
| Develop the I-LEAD agenda | CDC - Neranga, Jan, Herman
Finalize agenda
Translate training materials into French (if needed)
Create Glossary for technical terms
Create a folder with all materials available for participants with translated versions
Develop homework to assign before the I-LEAD workshop
Develop plan with addressing any unforseen challenges or changes to workshop structure, content, or delivery
4 | Trainer/speaker identification
Identify trainers/SMEs for training sessions
Recruitment for informatics trainers - consider language needs
Trainer/faculty recruitment and selection
Planning session for facilitators/trainers, meeting with POCs
Compile biosketches
| Share biosketches to organizing committee |  |  |  |  | To be shared with all the participants by I-LEAD D1
| Send meeting invites to speakers and moderators | CDC - Maria
| Obtain slides and materials from speakers for sessions | CDC - Maria
5 | Logistics
| Identify and secure venue for I-LEAD training | CDC - Maria
| Communicate venue entry requirements (if any) | CDC - Maria
Determine visa requirements
| Coordinate travel logistics (visas, flights, etc.) |  |  |  |  | To avoid show stoppers and to get the participants in the room
| Catering arrangements during I-LEAD | CDC - Maria
| Pre-I-LEAD venue walkthrough | CDC - Jan, Neranga
| Create and populate shared materials respository | CDC - Maria
Print certificates
Travel arrangements for participants
Identify and hire translators
6 | Post-I-LEAD Feedback and evaluation
| Create feedback forms | CDC - Maria
Distribute feedback forms
Analyze results
Status
green - implementation according to planned
yellow - delays or changes identified and being addressed
red - significant issues or delays that require problems solving

## Timeline Overview (hidden)
Process | Timeframe |  | Milestone
0. / 7. Logistics | Should begin 6 months pre-I-LEAD | 2024-01-01 | Venue (will set max participant headcount)
Food
Travel logistics (visas, approvals, etc.)
Funding secured
1. Marketing/Socializing | Should begin 6 months pre-I-LEAD | 2024-01-01 | Preliminary commitment by Country Teams
2. Onboarding | Should occur 4 months pre-I-LEAD | 2024-02-29 | Draft email to country teams to confirm attendance | Reach out to 4 countrues and confirm attendance, dates, agenda
Review the email draft with the interagency team
Send the email to country teams
Country Commitment to attend I-LEAD
3. Orientation | Should occur 3 months pre-I-LEAD | 2024-03-15 | Country Participants are selected (ahead of orientation)
In-country POC(s) identified
A list of interagency/interorganizational country content needs
Participants logistics
|  | 2024-03-29 | Orientation Webinar
4. Preparation: Organizing Team | Should occur 3 months pre-I-LEAD | 2024-03-15 | Agenda (draft) | Also ask country teams for their suggested agenda items
Speaker confirmation
Content coordination
Logistics
Feedback collection mechanism
Facilitator training
Organizing Team POC(s) for each country identified
5. Preparation: Participating Team | Should occur 2 months pre-I-LEAD | 2024-04-01 | Country presentation – introduction
Expedited ISHO
BYODDs
6. I-LEAD Week Material | Should begin to be finalized 1 month pre-I-LEAD | 2024-05-24 | Agenda (Final)
Session plans
Certificates
I-LEAD Week |  | June24-28?
Post I-LEAD AAR and Follow-up | Should happen within 4 weeks of I-LEAD week | July 1-5 | Recommendations for next I-LEAD
Leadership communications
Media communications (Internal/Public)
Initiate conversations around GEEKS (or other) project implementation

## Activity Tracker (hidden)
Activities | Why/details | Start date | Due Date | Status | Primary Responsible | Secondary Responsible | Notes
Participant Teams
Agency-level Leadership sensitization/approval |  | 2024-01-01 | 2024-02-01
Identify POC & agency POCs | Serves as overall point person for I-LEAD coordination, enables interagency communication | 2024-01-01 | 2024-02-01
Identify high-level issues to tackle during I-LEAD | Aids in selecting participants and developing initial agenda | 2024-01-01 | 2024-03-15
Identify/clarify funding |  | 2024-01-01 | 2024-03-20
Determine visa requirements |  | 2024-01-01 | 2024-03-15
Identify potential participants (USG, MOH, IPs) | Based on country issues, stakeholder groups | 2024-02-01 | 2024-03-15
coordinate travel logistics (visas, flights, etc.) | To avoid show stoppers and to get the participants in the room | 2024-03-01 | 2024-05-01
Attend Orientation webinar conducted by USG HQ | Kick-off point for I-LEAD work and participant expectation setting | 2024-03-01 | 2024-05-01
Review materials for action items/homework | The participating team will have an internal plan/agreement to review, do, discuss, agree and submit the homework before the I-LEAD | 2024-05-01 | 2024-06-01
conduct joint ISHO assessment (all participants) | Provide an opportunity to collaborate, build rapport, identify and prioritize the informatics gaps they want to focus | 2024-05-01 | 2024-06-01
Finalize ISHO results, country presentation and BYODDs |  | 2024-05-01 | 2024-06-01
Convene participants to develop country presentation and BYODDs |  | 2024-05-01 | 2024-06-01
Share biosketches to organizing committee | To be shared with all the participants by I-LEAD D1 | 2024-06-01 | 2024-06-15
Implementing Team
Confirm venue |  | 2024-02-21 | 2024-03-20 |  | CDC - Maria
Develop tailored breifing/sensitizaton material | Concept note | 2024-02-02 | 2024-03-06 | Complete | CDC - Maria | Jan, Nernaga, Herman
Develop a participant information packet |  |  | 2024-04-19 |  | CDC - Maria | USAID - Anja; CDC -Neranga
Develop RACI matrix for implementation team |  |  |  |  | CDC - Maria
Confirm target countries |  |  | 2024-02-21 | Complete | CDC - Herman |  | see Notes Tab
PCO and Agency-level Leadership sensitization/approval | Sensitize the Agency level leadership and obtain necessary approval | 2024-02-21 | 2024-03-15 | Complete | Jacob | Julianna
Send official invitation for country participation |  |  | 2024-03-15 |  | Jacob | Julianna, Herman | Need to have countries confirmed, H meeting with CDC BW 3/5, T, N, and H met with CDC DRC 2/28
Obtain confirmation of country attendence |  |  | 2024-03-29
Identify centralized communication model for implemntaton team | Can be a mailbox, distribution list, or individual. Allows participants to have a single contact for all key communication. | [5 empty] | ideal if it is
Identify and communicate venue entry requirements (if any) |  | 2024-02-21 | 2024-03-20 |  | CDC - Maria |  | https://docs.google.com/presentation/d/e/2PACX-1vTCYzMYDYC_kx9U7N01kWjGTx_AINFjzR5FcIZMwhrua0N8MphegBoUO4Atc8JluTbKvGSg5VM2PANj/pub?start=false&loop=false&delayms=3000&slide=id.g13bcf367c61_0_12
Identify/clarify funding | Both for implementation and country participation (may be on an organizational or individual level) | 2024-02-21 | 2024-03-20 |  |  |  | Country Offices are responsible for funding participant travel. There may be funds from the CoAg for venue support, plus CDC RW support.
Identify in-country POC | Serve as main contact/communication points in each country. Ideally one POC from each country who can communicate across agencies. If not possible, we should have in-country counterparts from the 3 agencies | 2024-02-21 | 2024-03-11 |  | CDC - Neranga | Julianna, Herman | Cross-agency collaboration can ahppen by CCs in email
Develop messaging for in-country POC | roles, responsibilities, timelines | 2024-02-21 | 2024-03-11 |  | CDC - Jan, Neranga | CDC - Maria
Monitor country team progress | Develop and implemnt plan for ensuring POCs/country teams will arrive prepared on the first day of training | 2024-02-21 | 2024-06-24 |  |  |  | includes travel arrangements, homework, biosketches
Compile high-level country issues to address in I-LEAD |  | 2024-02-21 | 2024-03-20 |  | CDC - Neranga
Review high-level country issues to address in I-LEAD |  | 2024-02-21 | 2024-03-20 |  | CDC - Neranga
Determine if translation will be needed | Oral and/or written (reading materials, slides) |  | 2024-02-21 |  | CDC - Maria |  | Likely French
Develop initial draft agenda | Based on country high-level issues |  | 2024-03-15 |  | CDC - Neranga, Jan, Herman
Develop learning objectives/talking points for sessions | Based on country high-level issues. Enables session refinement and speaker identification |  | 2024-03-29 |  | CDC - Neranga
Validate LOs and talking points |  |  | 2024-04-10
Identify agenda manager/POC |  |  | 2024-02-24 |  | CDC - Maria
Engage speakers | confirm interest and availability, convey logistics and key messages |  | 2024-06-03 |  | All?
Coordinate content within sessions | If multiple speakers, convene meeting to ensure no content overlap or gaps |  | 2024-06-14
Send meeting invites to speakers and moderators |  |  | 2024-06-17 |  | CDC - Maria
Obtain slides and materials from speakers for sessions |  |  | 2024-06-17 |  | CDC - Maria
create and populate shared materials respository |  |  | 2024-06-20 |  | CDC - Maria
Catering arrangements during I-LEAD |  |  | 2024-06-03 |  | CDC - Maria
Create feedback forms |  |  | 2024-06-14 |  | CDC - Maria
Compile biosketches |  |  | 2024-06-14
Finalize agenda |  |  | 2024-06-14
Print certificates |  |  | 2024-06-21
Pre-I-LEAD venue walkthrough |  |  | 2024-06-21 |  | CDC - Jan, Neranga
I-LEAD Week | June 24-28 (tenative)
July 15-19

## Preparation Checklist (hidden)
I-LEAD Preparation Check-list
Status | Action Items | Date | Person | Notes | Attachments | Parent item | Sub-item
Complete | Confirm participating countries
Complete | Confirm dates
Complete | Confirm location
Complete | Issue invitation/nomination packets
In progress | List of contact persons
In progress | Finalize I-LEAD agenda
In progress | Identify speakers
In progress | Prepare talking points for all sessions |  |  | Check on pre-recorded videos, presentations
Create and validate glossary
Communicate with speakers/discuss talking points
Send invititations to speakers
In progress | Identify facilitators and moderators
Send invitations to facilitators and moderators
Complete | Identify POCs
Complete | Identify (written) translation services | 2024-07-20
In progress | Translation of Written Materials
Send named info packets with an official infomation about the workshop, venue, logistics (translated)
Request access to the WHO assessment for participants
In progress | Identify (spoken, in-person) interpretation services | 2024-08-10
In progress | Catering | 2024-09-01
Finalized participants' list received
In progress | Set up shared drive with storing all materials for speakers and facilitators
In progress | Set up shared drive with storing all materials for participants
Complete | Orientation preparation: speakers, presentations (PPT)
Identify and prepare "homework" for participants
Orientation meeting with POCs
Orientation meetings with country teams
| Follow-up with participants after the orientation |  |  | email communication, ISHO assessment clarification, homework related questions, logistics
Travel package, certificates with signatures, name tags
Country pre-work
Participants' bios received (with correct spelled names)
| M&E plan for I-LEAD |  |  | Including evaluations during I-LEAD and post-I-LEAD analysis/assessment
Meeting with the implementing team (in person)
Print out cards for group activities, workbooks.

## Notes (hidden)
Core Implementation Team
Agency | Names
CDC | Maria, Neranga, Jan, Herman, Tad, Nicolas (?)
USAID | Julianna, Adeola, Anabel [May need to wait until countries are finalized for others]
DOD | Charles, Anne T
PATH | Caitlin, Lauren, Brianna
Country Participation:
Aiming for 3 to 5 countries based on ability to show impact of I-LEAD and resource constraints
Country | Status | Country POCs | Notes
Rwanda | confirmed
Eswatini | confirmed - USAID and CDC participation
4. DRC | unconfirmed - approached Nicolas (no response yet), priority country and opportunity to form a digital health strategy |  | Nicolas has a call on 2/29. If we get DRC or CI, Nicolas can support as a french speaker
3. Cote D'Ivoire | unconfirmed - need to ask Nicolas, seeking to build digital health portfolio and strong chair. Would be easier for USAID to engage with than DRC. |  | Will get an update from USAID 3/1 (Djibril, French-speaker)
2. Ghana | Confirmed - CDC regional office confirmed; may be good to prep for the next one or GEEKS. May be a future host country. USAID office has confirmed interest in attending, possibilty of hosting. There is a USAID RTC here (capacity = 30). |  | Si Branch CDC is interested, need to get approval
1. Botswana | USAID office has expressed interest and is a priority. CDC team has backed out.

## Communication plan (hidden)
Activity | Deliverable | Frequency | Priority | Responsibility | Preferred delivery method | Comments
Operational meetings | Meeting notes | Weekly | High |  | Team meeting
Technical meetings | Meeting notes | Weekly | High |  | Team meeting
Email communcations | Email communcations | As needed | High | Everyone | Email
Communication with country representatives | Invitation letters, invitation package | As needed | High |  | Email
Communication with speakers and trainers | Spreadsheet with sessions and speakers/facilitators I-LEAD Agenda Curriculum content/Activities for sessions Talking points | As needed | High |  | Shared folder on Teams Email
Communication with other involved parties: interpreters, logistics company etc. | Email communcations | As needed | High |  | Email